## Information
No | Variable | Value
1 | projectName | Database Upgrade
2 | goLiveDate | 2026-04-29
3 | prevTaskComment | Before 9 a.m.
4 | prevTaskStart | 08:00:00

## Timeline
No | Category | Predecessors | Start | Finish | Duration | Task | CheckPoint | Assignee
1 | Preparation | N/A | N/A | 9:00 | N/A | Announcement of cutover commencement | Notify all stakeholders of the start. | Client
2 | Preparation | N/A | N/A | 9:00 | N/A | Verification of network routing & firewall rules | Ensure connectivity between DB servers. | Infrastructure Team
3 | Preparation | 2 | 9:00 | 10:00 | 1:00 | Execution of pre-migration application jobs | Clear queues and finalise transactions. | Application Team
4 | Lockdown | 1 | N/A | 9:00 | N/A | Termination of user sessions & login suspension | Establish a static point for data consistency. | Client
5 | Data Backup | 4 | 9:00 | 11:00 | 2:00 | Full database backup & integrity verification | Create a restoration point for roll-back. | Infrastructure Team
6 | Execution | 3, 5 | 11:00 | 14:00 | 3:00 | Database schema migration & upgrade | Critical path task. | Infrastructure Team
7 | Execution | 6 | 14:00 | 16:00 | 2:00 | Application configuration & software upgrade | Update database connection strings. | Application Team
8 | Validation | 6 | 14:00 | 15:30 | 1:30 | DB index rebuilding & performance optimisation | Optimise performance after data transfer. | Infrastructure Team
9 | Validation | 7, 8 | 16:00 | 18:00 | 2:00 | Application Integration Testing (Smoke Test) | Joint verification for business resumption. | App Team & Client
10 | Post-Migration | 9 | 18:00 | 19:00 | 1:00 | Initialisation of monitoring & log analysis | Commence production environment monitoring | Infrastructure Team
11 | Post-Migration | 10 | 19:00 | 19:30 | 0:30 | Client's Approval Final authorisation for go-live | Formal sign-off for project completion. | Client